# 6. PROTOTYPE BUILD PLAN

## 6.1 Target: Build V1 in 90 Days for $10K-$25K

This is a functional prototype, not a production unit. It needs to: - Demonstrate the core concept (motorized cable-assisted stretching) - Be safe enough for supervised testing with real users - Collect data to validate the product thesis - Look credible enough to show investors and NFL/NBA training staff

## 6.2 Bill of Materials — Estimated

| Category | Item | Source | Est. Cost |
| --- | --- | --- | --- |
| Frame | 2”x2” steel square tube, welded | Local metal fab shop or 80/20 aluminum extrusion | $800-$1,500 |
| Motors (x4) | Brushless DC motor, 200W, 24V (e.g., ODrive-compatible BLDC motors) | Amazon / AliExpress / ODrive shop | $150 x 4 = $600 |
| Motor controllers (x4) | ODrive v3.6 or similar BLDC controller | ODrive Robotics | $120 x 4 = $480 |
| Gearboxes (x4) | Planetary gearbox, 20:1, NEMA 34 mount | Amazon / RobotShop | $80 x 4 = $320 |
| Cable spools (x4) | Custom machined aluminum drums, 6” dia | Local machine shop or 3D printed (metal fill) | $200 |
| Cables | 3/16” coated steel cable, 50 ft total | McMaster-Carr | $60 |
| Pulleys (x8) | Nylon/steel cable pulleys, bearing-mounted | McMaster-Carr / Amazon | $15 x 8 = $120 |
| Load cells (x4) | S-type load cell, 50 lb capacity | Amazon (e.g., DYLY-103) | $25 x 4 = $100 |
| Load cell amplifiers (x4) | HX711 or NAU7802 ADC boards | Amazon / SparkFun | $10 x 4 = $40 |
| Rotary encoders (x4) | Built into ODrive motor feedback | Included with motors | $0 |
| Depth camera | Intel RealSense D435i | Intel store / Amazon | $350 |
| Microcontroller | STM32F4 or ESP32-S3 board | Amazon / DigiKey | $30 |
| Single-board computer | Raspberry Pi 5 (8GB) or Jetson Orin Nano | Amazon / NVIDIA | $150-$250 |
| Touchscreen | 15.6” capacitive touch display, HDMI | Amazon | $200 |
| Power supply | 24V 30A switching PSU | Amazon / Mean Well | $80 |
| Cuffs + straps | Padded ankle/wrist cuffs with D-rings | Amazon (gym accessory cuffs) | $60 |
| Carabiners | Locking carabiners, climbing-rated | Amazon | $30 |
| Hip belt | Padded dip belt, modified | Amazon | $40 |
| E-stop buttons (x2) | Industrial mushroom head, NC | Amazon / DigiKey | $20 |
| Wiring, connectors, misc | JST connectors, 14AWG wire, cable ties, etc. | DigiKey / Amazon | $200 |
| Platform | Rubber anti-fatigue mat, cut to size | Amazon / Home Depot | $50 |
| Slip clutches (x4) | Torque-limiting coupling, set to 35 lb | McMaster-Carr | $40 x 4 = $160 |
| Software development | Your time + open-source libraries | — | $0 (sweat equity) |
| Fabrication labor | Welding, assembly (if outsourced) | Local fab shop | $1,000-$2,000 |
| Contingency | 15% buffer for surprises | — | $700-$1,200 |
|  |  | TOTAL | $5,800-$8,500 |

Note: This leaves $1,500-$16,500 of the budget for iteration, a second prototype, or professional industrial design consultation.

## 6.3 What Can Be Hacked Together (Off-the-Shelf)

- Frame: Use 80/20 aluminum T-slot extrusion instead of welded steel. Bolts together like an Erector Set. Faster to prototype, easy to modify, no welding required. Slightly more expensive but saves weeks of fab time.

- Motor + controller: The ODrive ecosystem is built for exactly this. BLDC motor + ODrive controller + encoder = position and torque control out of the box. Python API. Huge community.

- Cable spools: Start with 3D-printed PLA drums for early testing. Switch to machined aluminum once the diameter and geometry are validated.

- Cuffs: Buy standard gym ankle/wrist cuffs ($15-30/pair on Amazon, already padded with D-ring attachments). No need to custom-make these.

- Touchscreen UI: Run a web app on the Raspberry Pi. Use a browser in kiosk mode. Build the UI in React or even just Python + Flask with a simple HTML frontend. No native app needed.

- Pose estimation: MediaPipe Pose runs on a Raspberry Pi 5 at ~15 fps with the depth camera. Good enough for form checking — you don’t need 60 fps for stretching.

## 6.4 What Needs Custom Work

| Item | Why It’s Custom | Difficulty |
| --- | --- | --- |
| Cable spool drums | Need specific diameter + cable anchor point + mounting to gearbox shaft | Medium — CNC or good 3D printer |
| Pillar cable routing channels | Internal channels for cable to run through pillar tubes | Medium — may need tube cutting/drilling |
| Motor mounting brackets | Mount motor+gearbox+spool assembly inside the pillar | Low — simple bent sheet metal |
| Firmware (STM32/ESP32) | PID control loop, load cell reading, encoder reading, E-stop logic, serial communication to SBC | Medium — ~2 weeks of embedded dev |
| Stretch routine software | Sequencing engine, tension profiles per stretch, camera integration, UI | Medium-High — ~4-6 weeks of software dev |
| User profile + progress DB | SQLite on Pi, stores ROM history, user preferences | Low — standard web dev |

## 6.5 Prototype Timeline (90 Days)

| Week | Milestone |
| --- | --- |
| 1-2 | Order all parts. Design frame in CAD (Fusion 360). Design cable routing. |
| 3-4 | Build frame (80/20 extrusion). Mount pulleys. Bench-test one motor+spool+cable unit. |
| 5-6 | Integrate all 4 motor units into frame. Wire load cells and encoders. Basic firmware: manual motor control + force reading. |
| 7-8 | PID tension control working. User can clip in and feel controlled cable pull. E-stop functional. |
| 9-10 | Mount depth camera. Integrate MediaPipe pose estimation. Basic UI on touchscreen: start session, run stretch, end session. |
| 11-12 | Build 3-4 complete stretch routines. Tune tension profiles. Add form correction prompts. User testing with 5-10 athletes. |
| 13 (buffer) | Fix everything that broke during testing. Polish UI. Prepare for demo. |

## 6.6 Tools Needed

- 3D printer (for spool drums, brackets, cable guides — any FDM printer works)

- Basic hand tools (wrenches, Allen keys, drill)

- Soldering iron + multimeter

- Laptop for firmware development (Arduino IDE or PlatformIO for STM32/ESP32)

- Fusion 360 (free for startups) for CAD

- Access to a machine shop OR a good relationship with a local maker space